## Cultural RCG
Issue/Request | Requested by: | TWC Assignment/ Category Assignment* | Description | Status/Date Discussed | Current Action Items | Resolutions
Cultural Resource Plan | SCPRT, SCDNR, LSSRAC | Cultural Resources RCG | A plan should be developed in coordination with appropriate resource agencies to identify and protect the many known and unknown cultural resources located within the project boundaries. | October 14, 2005 - Group discussed Stage 1 survey activities as well as reviewed what will take place during Stage 2 intensive surveys. September 8, 2006 - group reviewed progress of Stage 2 surveys. Survey work ongoing. March 2, 2007- group reviewed initial findings of stage 2 surveys. Draft Stage 2 report has been submitted to SCE&G, SHPO and other consulting agencies. Developing a plan for resolving adverse effects occurring at the site 38LX531. | Develop a plan for resolving adverse effects occurring at the site 38LX531. • Create a list of categorical exclusions in conjunction with the Operations and Lake and Land Management RCGs. • Develop general recommendations for inclusion in the HPMP. | Ongoing